## dozer
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Dozer Productivity Data Records
|  |  |  | Form - 1 | [12 empty] | MPDM - Delay
[10 empty] | Blade Measurement | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Dozer Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Dozer Blade Type (S, U, SU, C) | Task Type | Description | Soil Type | H | W | L | Unit | Blad Load (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 101 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 54
|  |  |  | 102 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 58
|  |  |  | 103 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 104 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 342 | [5 empty] | 279
|  |  |  | 105 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 38
|  |  |  | 106 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 67
|  |  |  | 107 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 81
|  |  |  | 108 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 83
|  |  |  | 109 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 46
|  |  |  | 110 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 54
|  |  |  | 111 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 107
|  |  |  | 112 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 98
|  |  |  | 113 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 87
|  |  |  | 114 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 82
|  |  |  | 115 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 76
|  |  |  | 116 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 68
|  |  |  | 117 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 82
|  |  |  | 118 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 81
|  |  |  | 119 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 64
|  |  |  | 120 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 57
|  |  |  | 121 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 54
|  |  |  | 122 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 58
|  |  |  | 123 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 59
|  |  |  | 124 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 61
|  |  |  | 125 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 71
|  |  |  | 126 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 87
|  |  |  | 127 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 54
|  |  |  | 128 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 129 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 55
|  |  |  | 130 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 51
|  |  |  | 131 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 48
|  |  |  | 132 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 71
|  |  |  | 133 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 134 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 44
|  |  |  | 135 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 39
|  |  |  | 136 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 93
|  |  |  | 137 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 71
|  |  |  | 138 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 48
|  |  |  | 139 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 91
|  |  |  | 140 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 43
|  |  |  | 141 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 142 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 68
|  |  |  | 143 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 79
|  |  |  | 144 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 71
|  |  |  | 145 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 73
|  |  |  | 146 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 406 |  |  |  |  | 325
|  |  |  | 147 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 73
|  |  |  | 148 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 63
|  |  |  | 149 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 150 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 71
|  |  |  | 151 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 38
|  |  |  | 152 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 34
|  |  |  | 153 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 154 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 38
|  |  |  | 155 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 61
|  |  |  | 156 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 67
|  |  |  | 157 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 46
|  |  |  | 158 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 48
|  |  |  | 159 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 29
|  |  |  | 160 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 28
|  |  |  | 161 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 162 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 163 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 91
|  |  |  | 164 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 82
|  |  |  | 165 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 87
|  |  |  | 166 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 91
|  |  |  | 167 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 108
|  |  |  | 168 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 114
|  |  |  | 169 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 96
|  |  |  | 170 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 171 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 45
|  |  |  | 172 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 57
|  |  |  | 173 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 65
|  |  |  | 174 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 64
|  |  |  | 175 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 79
|  |  |  | 176 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 81
|  |  |  | 177 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 42
|  |  |  | 178 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 41
|  |  |  | 179 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 53
|  |  |  | 180 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 59
|  |  |  | 181 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 48
|  |  |  | 182 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 56
|  |  |  | 183 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 47
|  |  |  | 184 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 84
|  |  |  | 185 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 89
|  |  |  | 186 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 92
|  |  |  | 187 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 188 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 46
|  |  |  | 189 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 54
|  |  |  | 190 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 68
|  |  |  | 191 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 69
|  |  |  | 192 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 62
|  |  |  | 193 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 78
|  |  |  | 194 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 91
|  |  |  | 195 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 578 |  |  | 463
|  |  |  | 196 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 73
|  |  |  | 197 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 109
|  |  |  | 198 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 98
|  |  |  | 199 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 88
|  |  |  | 200 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.2 |  |  | 43

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
| Form - 4 | [6 empty] | Delay
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
[6 empty] | 101 | 54
[6 empty] | 102 | 58
[6 empty] | 103 | 56
[6 empty] | 104 | 342 |  |  |  |  | 279
[6 empty] | 105 | 38
[6 empty] | 106 | 67
[6 empty] | 107 | 81
[6 empty] | 108 | 83
[6 empty] | 109 | 46
[6 empty] | 110 | 54
[6 empty] | 111 | 107
[6 empty] | 112 | 98
[6 empty] | 113 | 87
[6 empty] | 114 | 82
[6 empty] | 115 | 76
[6 empty] | 116 | 68
[6 empty] | 117 | 82
[6 empty] | 118 | 81
[6 empty] | 119 | 64
[6 empty] | 120 | 57
[6 empty] | 121 | 54
[6 empty] | 122 | 58
[6 empty] | 123 | 59
[6 empty] | 124 | 61
[6 empty] | 125 | 71
[6 empty] | 126 | 87
[6 empty] | 127 | 54
[6 empty] | 128 | 56
[6 empty] | 129 | 55
[6 empty] | 130 | 51
[6 empty] | 131 | 48
[6 empty] | 132 | 71
[6 empty] | 133 | 78
[6 empty] | 134 | 44
[6 empty] | 135 | 39
[6 empty] | 136 | 93
[6 empty] | 137 | 71
[6 empty] | 138 | 48
[6 empty] | 139 | 91
[6 empty] | 140 | 43
[6 empty] | 141 | 56
[6 empty] | 142 | 68
[6 empty] | 143 | 79
[6 empty] | 144 | 71
[6 empty] | 145 | 73
[6 empty] | 146 | 406 |  |  |  | 325
[6 empty] | 147 | 73
[6 empty] | 148 | 63
[6 empty] | 149 | 78
[6 empty] | 150 | 71
[6 empty] | 151 | 38
[6 empty] | 152 | 34
[6 empty] | 153 | 56
[6 empty] | 154 | 38
[6 empty] | 155 | 61
[6 empty] | 156 | 67
[6 empty] | 157 | 46
[6 empty] | 158 | 48
[6 empty] | 159 | 29
[6 empty] | 160 | 28
[6 empty] | 161 | 56
[6 empty] | 162 | 78
[6 empty] | 163 | 91
[6 empty] | 164 | 82
[6 empty] | 165 | 87
[6 empty] | 166 | 91
[6 empty] | 167 | 108
[6 empty] | 168 | 114
[6 empty] | 169 | 96
[6 empty] | 170 | 78
[6 empty] | 171 | 45
[6 empty] | 172 | 57
[6 empty] | 173 | 65
[6 empty] | 174 | 64
[6 empty] | 175 | 79
[6 empty] | 176 | 81
[6 empty] | 177 | 42
[6 empty] | 178 | 41
[6 empty] | 179 | 53
[6 empty] | 180 | 59
[6 empty] | 181 | 48
[6 empty] | 182 | 56
[6 empty] | 183 | 47
[6 empty] | 184 | 84
[6 empty] | 185 | 89
[6 empty] | 186 | 92
[6 empty] | 187 | 78
[6 empty] | 188 | 46
[6 empty] | 189 | 54
[6 empty] | 190 | 68
[6 empty] | 191 | 69
[6 empty] | 192 | 62
[6 empty] | 193 | 78
[6 empty] | 194 | 91
[6 empty] | 195 | 578 |  | 463
[6 empty] | 196 | 73
[6 empty] | 197 | 109
[6 empty] | 198 | 98
[6 empty] | 199 | 88
[6 empty] | 200 | 43

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | Zond rock fill
Data Collector |  | Estibel agegne | Data Count | 22 |  | Date | 04/06/2017E.C
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | Record | 2.07 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 1 oprater,1 helper,1/19 forman | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | Record | 5 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | observation | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | interview | 13 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | observation | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | observation | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | observation | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | Record | 4.24 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | Record | 9,18 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | Record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | Record | 29,37 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | Record | 23,32 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | ro | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).