## dozer
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Dozer Productivity Data Records
|  |  |  | Form - 1 | [12 empty] | MPDM - Delay
[10 empty] | Blade Measurement | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Dozer Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Dozer Blade Type (S, U, SU, C) | Task Type | Description | Soil Type | H | W | L | Unit | Blad Load (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
05/06/2017E.C | 1 | Rudolf derbie | 1 | 1 | 1/10 forman,1 oprater,1 helper | SU | zoned rock fill |  | clay and gravel | 1.3 | 0.6 | 3.8 | m |  | 82
|  |  |  | 2 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 3 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 103
|  |  |  | 4 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 116
|  |  |  | 5 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 6 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 49
|  |  |  | 7 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 131
|  |  |  | 8 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 134
|  |  |  | 9 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 140
|  |  |  | 10 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 53
|  |  |  | 11 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 97
|  |  |  | 12 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 54
|  |  |  | 13 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 93
|  |  |  | 14 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 91
|  |  |  | 15 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 99
|  |  |  | 16 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 124
|  |  |  | 17 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 146
|  |  |  | 18 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 92
|  |  |  | 19 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 20 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 72
|  |  |  | 21 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 78
|  |  |  | 22 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 71
|  |  |  | 23 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 79
|  |  |  | 24 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 83
|  |  |  | 25 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 126
|  |  |  | 26 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 93
|  |  |  | 27 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 81
|  |  |  | 28 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 126
|  |  |  | 29 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 129
|  |  |  | 30 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 55
|  |  |  | 31 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 138
|  |  |  | 32 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 106
|  |  |  | 33 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 125
|  |  |  | 34 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 91
|  |  |  | 35 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 126
|  |  |  | 36 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 91
|  |  |  | 37 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 125
|  |  |  | 38 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 119
|  |  |  | 39 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 100
|  |  |  | 40 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 119
|  |  |  | 41 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 134
|  |  |  | 42 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 129
|  |  |  | 43 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 118
|  |  |  | 44 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 45 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 80
|  |  |  | 46 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 97
|  |  |  | 47 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 46
|  |  |  | 48 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 49 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 132
|  |  |  | 50 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 35
|  |  |  | 51 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 133
|  |  |  | 52 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 99
|  |  |  | 53 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 115
|  |  |  | 54 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 53
|  |  |  | 55 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 86
|  |  |  | 56 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 83
|  |  |  | 57 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 69
|  |  |  | 58 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 108
|  |  |  | 59 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 34
|  |  |  | 60 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 53
|  |  |  | 61 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 127
|  |  |  | 62 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 94
|  |  |  | 63 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 57
|  |  |  | 64 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 41
|  |  |  | 65 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 45
|  |  |  | 66 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 51
|  |  |  | 67 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 76
|  |  |  | 68 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 63
|  |  |  | 69 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 122
|  |  |  | 70 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 111
|  |  |  | 71 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 81
|  |  |  | 72 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 67
|  |  |  | 73 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 54
|  |  |  | 74 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 60
|  |  |  | 75 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 68
|  |  |  | 76 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 65
|  |  |  | 77 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 81
|  |  |  | 78 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 87
|  |  |  | 79 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 57
|  |  |  | 80 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 65
|  |  |  | 81 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 77
|  |  |  | 82 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 74
|  |  |  | 83 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 65
|  |  |  | 84 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 83
|  |  |  | 85 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 50
|  |  |  | 86 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 43
|  |  |  | 87 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 61
|  |  |  | 88 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 40
|  |  |  | 89 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 57
|  |  |  | 90 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 91
|  |  |  | 91 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 59
|  |  |  | 92 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 123
|  |  |  | 93 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 52
|  |  |  | 94 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 135
|  |  |  | 95 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 107
|  |  |  | 96 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 43
|  |  |  | 97 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 130
|  |  |  | 98 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 74
|  |  |  | 99 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 83
|  |  |  | 100 |  |  |  |  | clay and gravel | 1.3 | 0.6 | 3.8 |  |  | 43

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
| Form - 4 | [6 empty] | Delay
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
05/06/2017E.C | 1 | Rudolf derbie | sec |  |  | 1 | 82
[6 empty] | 2 | 94
[6 empty] | 3 | 103
[6 empty] | 4 | 116
[6 empty] | 5 | 94
[6 empty] | 6 | 49
[6 empty] | 7 | 131
[6 empty] | 8 | 134
[6 empty] | 9 | 140
[6 empty] | 10 | 53
[6 empty] | 11 | 97
[6 empty] | 12 | 54
[6 empty] | 13 | 93
[6 empty] | 14 | 91
[6 empty] | 15 | 99
[6 empty] | 16 | 124
[6 empty] | 17 | 146
[6 empty] | 18 | 92
[6 empty] | 19 | 94
[6 empty] | 20 | 72
[6 empty] | 21 | 78
[6 empty] | 22 | 71
[6 empty] | 23 | 79
[6 empty] | 24 | 83
[6 empty] | 25 | 126
[6 empty] | 26 | 93
[6 empty] | 27 | 81
[6 empty] | 28 | 126
[6 empty] | 29 | 129
[6 empty] | 30 | 55
[6 empty] | 31 | 138
[6 empty] | 32 | 106
[6 empty] | 33 | 125
[6 empty] | 34 | 91
[6 empty] | 35 | 126
[6 empty] | 36 | 91
[6 empty] | 37 | 125
[6 empty] | 38 | 119
[6 empty] | 39 | 100
[6 empty] | 40 | 119
[6 empty] | 41 | 134
[6 empty] | 42 | 129
[6 empty] | 43 | 118
[6 empty] | 44 | 94
[6 empty] | 45 | 80
[6 empty] | 46 | 97
[6 empty] | 47 | 46
[6 empty] | 48 | 94
[6 empty] | 49 | 132
[6 empty] | 50 | 35
[6 empty] | 51 | 133
[6 empty] | 52 | 99
[6 empty] | 53 | 115
[6 empty] | 54 | 53
[6 empty] | 55 | 86
[6 empty] | 56 | 83
[6 empty] | 57 | 69
[6 empty] | 58 | 108
[6 empty] | 59 | 34
[6 empty] | 60 | 53
[6 empty] | 61 | 127
[6 empty] | 62 | 94
[6 empty] | 63 | 57
[6 empty] | 64 | 41
[6 empty] | 65 | 45
[6 empty] | 66 | 51
[6 empty] | 67 | 76
[6 empty] | 68 | 63
[6 empty] | 69 | 122
[6 empty] | 70 | 111
[6 empty] | 71 | 81
[6 empty] | 72 | 67
[6 empty] | 73 | 54
[6 empty] | 74 | 60
[6 empty] | 75 | 68
[6 empty] | 76 | 65
[6 empty] | 77 | 81
[6 empty] | 78 | 87
[6 empty] | 79 | 57
[6 empty] | 80 | 65
[6 empty] | 81 | 77
[6 empty] | 82 | 74
[6 empty] | 83 | 65
[6 empty] | 84 | 83
[6 empty] | 85 | 50
[6 empty] | 86 | 43
[6 empty] | 87 | 61
[6 empty] | 88 | 40
[6 empty] | 89 | 57
[6 empty] | 90 | 91
[6 empty] | 91 | 59
[6 empty] | 92 | 123
[6 empty] | 93 | 52
[6 empty] | 94 | 135
[6 empty] | 95 | 107
[6 empty] | 96 | 43
[6 empty] | 97 | 130
[6 empty] | 98 | 74
[6 empty] | 99 | 83
[6 empty] | 100 | 43

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | Earth excavation
Data Collector |  | Rudolf derbie | Data Count | 16 |  | Date | 05/06/2017E.C
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.11 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 0.11 forman,1 oprater,1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 2 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | record | 5 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 2 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | interview |  | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 2 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | interview | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | interview | 0 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | observation | 10 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | interview | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | record | 6.7 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 6,37 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 50,65 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 24,32 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | record | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | record | 0 | Range (0 -38) | Over all project activities (besides the one under study).