## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 301 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3 | 0.61 |  |  | 1.3 | 19
|  |  |  | 302 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3 | 0.61 |  |  | 1.3 | 21
|  |  |  | 303 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3 | 0.61 |  |  | 1.3 | 25
|  |  |  | 304 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 305 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 26
|  |  |  | 306 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 25
|  |  |  | 307 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 24
|  |  |  | 308 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 24
|  |  |  | 309 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 25
|  |  |  | 310 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3 | 0.61 |  |  | 1.3 | 32
|  |  |  | 311 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 26
|  |  |  | 312 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 313 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 314 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 315 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 316 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 317 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 36
|  |  |  | 318 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 319 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 320 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 321 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 92
|  |  |  | 322 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 323 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 324 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 325 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 326 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 327 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 23
|  |  |  | 328 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 329 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 88
|  |  |  | 330 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 331 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 31
|  |  |  | 332 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 33
|  |  |  | 333 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 30
|  |  |  | 334 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 335 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 336 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 28
|  |  |  | 337 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 28
|  |  |  | 338 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 76
|  |  |  | 339 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 340 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 28
|  |  |  | 341 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 31
|  |  |  | 342 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 343 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 344 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 345 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 346 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 347 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 100
|  |  |  | 348 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 349 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 350 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 351 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 352 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 353 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 354 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 355 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 311 | [5 empty] | 279
|  |  |  | 356 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 357 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 358 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 359 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 28
|  |  |  | 360 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 32
|  |  |  | 361 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 362 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 82
|  |  |  | 363 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 364 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 19
|  |  |  | 365 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 20
|  |  |  | 366 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 17
|  |  |  | 367 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 21
|  |  |  | 368 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 20
|  |  |  | 369 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 22
|  |  |  | 370 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 93
|  |  |  | 371 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 32
|  |  |  | 372 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 373 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 374 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 31
|  |  |  | 375 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 376 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 35
|  |  |  | 377 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 378 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 475 | [5 empty] | 459
|  |  |  | 379 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 380 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 23
|  |  |  | 381 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 31
|  |  |  | 382 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 383 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 37
|  |  |  | 384 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 42
|  |  |  | 385 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 386 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 387 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 388 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 80
|  |  |  | 389 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 390 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 391 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 392 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 31
|  |  |  | 393 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 32
|  |  |  | 394 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 395 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 29
|  |  |  | 396 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 397 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 105
|  |  |  | 398 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 35
|  |  |  | 399 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 26
|  |  |  | 400 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 43

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 301 | 19
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 302 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 303 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 304 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 305 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 306 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 307 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 308 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 309 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 310 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 311 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 312 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 313 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 314 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 315 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 316 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 317 | 36
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 318 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 319 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 320 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 321 | 92
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 322 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 323 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 324 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 325 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 326 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 327 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 328 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 329 | 88
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 330 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 331 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 332 | 33
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 333 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 334 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 335 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 336 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 337 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 338 | 76
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 339 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 340 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 341 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 342 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 343 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 344 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 345 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 346 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 347 | 100
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 348 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 349 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 350 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 351 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 352 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 353 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 354 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 355 | 311 |  |  |  |  | 279
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 356 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 357 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 358 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 359 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 360 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 361 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 362 | 82
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 363 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 364 | 19
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 365 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 366 | 17
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 367 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 368 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 369 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 370 | 93
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 371 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 372 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 373 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 374 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 375 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 376 | 35
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 377 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 378 | 475 |  |  |  |  | 459
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 379 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 380 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 381 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 382 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 383 | 37
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 384 | 42
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 385 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 386 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 387 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 388 | 80
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 389 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 390 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 391 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 392 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 393 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 394 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 395 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 396 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 397 | 105
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 398 | 35
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 399 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 400 | 43

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic excavator
Data Collector |  | Yared Girmaw | Data Count | 7 |  | Date | 06_07_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.07 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.07 foeman, 1 opetator, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 11 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 2 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 6.5 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 3 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 11,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 18, 25 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19, 23 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).