## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
17_05_2017 | 1 | Cherinet Bisetegn | 2 | 1 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 2083 | 0.020221 |  |  |  |  | 2040
|  |  |  | 2 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 63
|  |  |  | 3 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 68
|  |  |  | 4 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 5 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 6 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 7 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 36
|  |  |  | 8 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 9 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 89
|  |  |  | 10 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 11 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 82 |  |  |  | 49
|  |  |  | 12 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 55
|  |  |  | 13 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 127 | [5 empty] | 100
|  |  |  | 14 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 34
|  |  |  | 15 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 16 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 32
|  |  |  | 17 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 18 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 41
|  |  |  | 19 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 20 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 30
|  |  |  | 21 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 310 | [5 empty] | 283
|  |  |  | 22 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 34
|  |  |  | 23 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 320 | [5 empty] | 298
|  |  |  | 24 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 25 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 20
|  |  |  | 26 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 18
|  |  |  | 27 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 28 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 20
|  |  |  | 29 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 30 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 31 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 32 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 33 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 34 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 35 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 18
|  |  |  | 36 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 20
|  |  |  | 37 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 73
|  |  |  | 38 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 39 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 40 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 41 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 42 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 43 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 56
|  |  |  | 44 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 84
|  |  |  | 45 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 46 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 40
|  |  |  | 47 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 48 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 49 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 50 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 64
|  |  |  | 51 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 52 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 53 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 54 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 86
|  |  |  | 55 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 89
|  |  |  | 56 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 57 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 58 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 59 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 60 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 61 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 62 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 63 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 62
|  |  |  | 64 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 46
|  |  |  | 65 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 47
|  |  |  | 66 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 67 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 68 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 69 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 70 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 71 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 72 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 73 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 74 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 75 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 76 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 68
|  |  |  | 77 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 78 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 79 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 126
|  |  |  | 80 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 63
|  |  |  | 81 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 86
|  |  |  | 82 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 73
|  |  |  | 83 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 89
|  |  |  | 84 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 67
|  |  |  | 85 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 56
|  |  |  | 86 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 54
|  |  |  | 87 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 38
|  |  |  | 88 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 89 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 90 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 91 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 92 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 90 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 93 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 97
|  |  |  | 94 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 95 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 96 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 97 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 98 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 99 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 100 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 18

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 1 | 2083 |  |  |  |  | 2040
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 2 | 63
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 3 | 68
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 4 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 5 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 6 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 7 | 36
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 8 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 9 | 89
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 10 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 11 | 82 |  |  | 49
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 12 | 55
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 13 | 127 |  |  |  |  | 100
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 14 | 34
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 15 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 16 | 32
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 17 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 18 | 41
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 19 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 20 | 30
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 21 | 310 |  |  |  |  | 283
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 22 | 34
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 23 | 320 |  |  |  |  | 298
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 24 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 25 | 20
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 26 | 18
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 27 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 28 | 20
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 29 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 30 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 31 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 32 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 33 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 34 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 35 | 18
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 36 | 20
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 37 | 73
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 38 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 39 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 40 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 41 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 42 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 43 | 56
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 44 | 84
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 45 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 46 | 40
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 47 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 48 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 49 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 50 | 64
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 51 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 52 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 53 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 54 | 86
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 55 | 89
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 56 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 57 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 58 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 59 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 60 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 61 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 62 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 63 | 62
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 64 | 46
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 65 | 47
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 66 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 67 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 68 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 69 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 70 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 71 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 72 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 73 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 74 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 75 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 76 | 68
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 77 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 78 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 79 | 126
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 80 | 63
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 81 | 86
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 82 | 73
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 83 | 89
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 84 | 67
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 85 | 56
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 86 | 54
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 87 | 38
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 88 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 89 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 90 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 91 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 92 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 93 | 97
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 94 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 95 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 96 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 97 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 98 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 99 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 100 | 18

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 01- soft rock excavation using hydraulic excavator
Data Collector |  | Cherinet Bisetegn | Data Count | 12 |  | Date | 17_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | observation | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 1 operator, 1 helper, 1/11 foreman | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 3 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 8 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | ask | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | ask | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | ask | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | ask | 13 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | ask | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | ask | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | observation | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 1 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 11,19 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 17,23 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 28,29 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 40 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).