## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 401 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 402 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 2
|  |  |  | 403 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 404 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 405 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 21
|  |  |  | 406 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 216 | [5 empty] | 185
|  |  |  | 407 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 408 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 409 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 410 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 411 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 412 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 413 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 26
|  |  |  | 414 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 75
|  |  |  | 415 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 416 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 417 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 20
|  |  |  | 418 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 21
|  |  |  | 419 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 18
|  |  |  | 420 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 421 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 422 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 235 | [5 empty] | 205
|  |  |  | 423 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 424 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 425 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 426 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 427 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 428 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 429 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 430 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 98
|  |  |  | 431 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 432 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 433 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 434 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 435 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 436 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 437 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 249 | [5 empty] | 227
|  |  |  | 438 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 15
|  |  |  | 439 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 21
|  |  |  | 440 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 19
|  |  |  | 441 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 442 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 443 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 444 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 445 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 120
|  |  |  | 446 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 17
|  |  |  | 447 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 448 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 449 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 450 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 451 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 78
|  |  |  | 452 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 453 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 454 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 455 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 456 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 457 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 275 | [5 empty] | 247
|  |  |  | 458 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 459 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 460 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 24
|  |  |  | 461 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 462 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 26
|  |  |  | 463 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.7 | 0.53 |  |  | 1.7 | 26
|  |  |  | 464 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 465 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 466 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 467 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 468 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 469 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 28
|  |  |  | 470 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 29
|  |  |  | 471 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 472 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 473 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 474 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 475 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 476 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 477 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 478 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 479 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 480 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 481 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 298 | [5 empty] | 273
|  |  |  | 482 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 483 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 30
|  |  |  | 484 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 29
|  |  |  | 485 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 486 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 487 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 488 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 489 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 21
|  |  |  | 490 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 491 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 492 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 301 | [5 empty] | 287
|  |  |  | 493 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 494 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 495 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 496 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 2 | 0.53 |  |  | 1.7 | 97
|  |  |  | 497 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 498 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 499 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 1020 |  |  |  | 988
|  |  |  | 500 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 24

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 401 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 402 | 2
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 403 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 404 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 405 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 406 | 216 |  |  |  |  | 185
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 407 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 408 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 409 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 410 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 411 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 412 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 413 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 414 | 75
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 415 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 416 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 417 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 418 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 419 | 18
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 420 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 421 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 422 | 235 |  |  |  |  | 205
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 423 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 424 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 425 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 426 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 427 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 428 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 429 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 430 | 98
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 431 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 432 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 433 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 434 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 435 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 436 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 437 | 249 |  |  |  |  | 227
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 438 | 15
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 439 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 440 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 441 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 442 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 443 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 444 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 445 | 120
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 446 | 17
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 447 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 448 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 449 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 450 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 451 | 78
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 452 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 453 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 454 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 455 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 456 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 457 | 275 |  |  |  |  | 247
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 458 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 459 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 460 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 461 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 462 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 463 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 464 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 465 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 466 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 467 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 468 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 469 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 470 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 471 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 472 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 473 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 474 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 475 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 476 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 477 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 478 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 479 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 480 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 481 | 298 |  |  |  |  | 273
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 482 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 483 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 484 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 485 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 486 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 487 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 488 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 489 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 490 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 491 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 492 | 301 |  |  |  |  | 287
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 493 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 494 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 495 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 496 | 97
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 497 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 498 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 499 | 1020 |  |  | 988
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 500 | 24

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic exvavator
Data Collector |  | Yared Girmaw | Data Count | 2 |  | Date | 28_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.083 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.08 foreman, 1 op, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | count | 15 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 12 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 2 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 5 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 18 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 5 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 10,24 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 50,67 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 18,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).