## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 501 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 502 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 503 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 36
|  |  |  | 504 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 505 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 506 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 507 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 508 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 509 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 510 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 511 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 512 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 21
|  |  |  | 513 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 121
|  |  |  | 514 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 18
|  |  |  | 515 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 516 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 517 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 21
|  |  |  | 518 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 307 | [5 empty] | 285
|  |  |  | 519 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 520 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 21
|  |  |  | 521 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 522 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 523 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 524 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 525 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 526 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 527 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 91
|  |  |  | 528 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 30
|  |  |  | 529 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 530 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 531 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 532 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 533 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 277 | [5 empty] | 252
|  |  |  | 534 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 535 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 536 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 537 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 538 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 539 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 540 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 87
|  |  |  | 541 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 542 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 29
|  |  |  | 543 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 544 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 545 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 546 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 547 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 548 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 122
|  |  |  | 549 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 31
|  |  |  | 550 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 551 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 552 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 553 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 554 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 555 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 31
|  |  |  | 556 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 2.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 557 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 405 | [5 empty] | 381
|  |  |  | 558 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 559 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 560 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 561 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 33
|  |  |  | 562 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 563 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 18
|  |  |  | 564 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 565 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 566 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 95
|  |  |  | 567 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 568 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 569 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 570 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 92
|  |  |  | 571 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 572 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 573 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 2.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 574 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 575 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 2.2 | 0.53 |  |  | 1.7 | 22

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 501 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 502 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 503 | 36
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 504 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 505 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 506 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 507 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 508 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 509 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 510 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 511 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 512 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 513 | 121
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 514 | 18
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 515 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 516 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 517 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 518 | 307 |  |  |  |  | 285
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 519 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 520 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 521 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 522 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 523 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 524 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 525 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 526 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 527 | 91
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 528 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 529 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 530 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 531 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 532 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 533 | 277 |  |  |  |  | 252
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 534 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 535 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 536 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 537 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 538 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 539 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 540 | 87
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 541 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 542 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 543 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 544 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 545 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 546 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 547 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 548 | 122
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 549 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 550 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 551 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 552 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 553 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 554 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 555 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 556 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 557 | 405 |  |  |  |  | 381
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 558 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 559 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 560 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 561 | 33
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 562 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 563 | 18
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 564 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 565 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 566 | 95
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 567 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 568 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 569 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 570 | 92
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 571 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 572 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 573 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 574 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 575 | 22

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic exvavator
Data Collector |  | Yared Girmaw | Data Count | 2 |  | Date | 28_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.083 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.08 foreman, 1 op, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | count | 15 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 12 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 2 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 5 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 18 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 5 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 10,24 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 50,67 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 18,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).