## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 12
Data Collector |  | Temesgen Atalay | Data Count | 1 |  | Date | 22_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 1/10 foreman 1 helper, 1 operator | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | record | 50 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | asking | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | observation | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | record | 0.42 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | count | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 8,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 53,60 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | record | 0 | Range (0 -38) | Over all project activities (besides the one under study).