## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 401 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 402 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 51
|  |  |  | 403 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 404 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 406 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 121
|  |  |  | 407 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 36
|  |  |  | 408 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 42
|  |  |  | 409 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 28
|  |  |  | 410 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 411 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 412 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 413 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 99
|  |  |  | 414 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 31
|  |  |  | 415 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 416 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 417 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 19
|  |  |  | 418 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 21
|  |  |  | 419 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 20
|  |  |  | 420 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 22
|  |  |  | 421 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 87
|  |  |  | 422 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 423 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 424 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 28
|  |  |  | 425 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 426 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 31
|  |  |  | 427 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 428 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 429 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 30
|  |  |  | 430 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 3 | 0.61 |  |  | 1.3 | 32
|  |  |  | 431 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 75
|  |  |  | 432 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 433 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 434 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 435 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 30
|  |  |  | 436 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 437 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 438 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 30
|  |  |  | 439 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 440 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 96
|  |  |  | 441 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 442 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 443 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 444 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 445 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 446 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 447 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 448 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 449 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 102
|  |  |  | 450 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 2.5 | 0.61 |  |  | 1.3 | 28
|  |  |  | 451 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 452 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 311 | [5 empty] | 290
|  |  |  | 453 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 454 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 29
|  |  |  | 455 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 456 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 87
|  |  |  | 457 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 28
|  |  |  | 458 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 459 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 460 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 461 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 28
|  |  |  | 462 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 25
|  |  |  | 463 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 73
|  |  |  | 464 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 31
|  |  |  | 465 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 30
|  |  |  | 466 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 467 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 32
|  |  |  | 468 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 469 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 29
|  |  |  | 470 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 31
|  |  |  | 471 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 27
|  |  |  | 472 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 473 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 3.2 | 0.61 |  |  | 1.3 | 67
|  |  |  | 474 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 29
|  |  |  | 475 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 476 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 36
|  |  |  | 477 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 305 | [5 empty] | 289
|  |  |  | 478 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 30
|  |  |  | 479 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 22
|  |  |  | 480 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 21
|  |  |  | 481 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 17
|  |  |  | 482 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 112
|  |  |  | 483 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 484 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 28
|  |  |  | 485 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 486 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 27
|  |  |  | 487 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 25
|  |  |  | 488 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 25
|  |  |  | 489 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 490 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 24
|  |  |  | 491 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 492 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 23
|  |  |  | 493 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 98
|  |  |  | 494 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 495 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 496 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 81
|  |  |  | 497 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 28
|  |  |  | 498 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.9 | 0.61 |  |  | 1.3 | 26
|  |  |  | 499 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 17
|  |  |  | 500 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 45 | 3.2 | 0.61 |  |  | 1.3 | 19
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35
|  |  |  | 405 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3.2 | 0.61 |  |  | 1.3 | 35

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 401 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 402 | 51
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 403 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 404 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 405 | 35
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 406 | 121
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 407 | 36
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 408 | 42
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 409 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 410 | 35
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 411 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 412 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 413 | 99
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 414 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 415 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 416 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 417 | 19
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 418 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 419 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 420 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 421 | 87
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 422 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 423 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 424 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 425 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 426 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 427 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 428 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 429 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 430 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 431 | 75
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 432 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 433 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 434 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 435 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 436 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 437 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 438 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 439 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 440 | 96
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 441 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 442 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 443 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 444 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 445 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 446 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 447 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 448 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 449 | 102
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 450 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 451 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 452 | 311 |  |  |  |  | 290
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 453 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 454 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 455 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 456 | 87
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 457 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 458 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 459 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 460 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 461 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 462 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 463 | 73
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 464 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 465 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 466 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 467 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 468 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 469 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 470 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 471 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 472 | 35
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 473 | 67
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 474 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 475 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 476 | 36
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 477 | 305 |  |  |  |  | 289
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 478 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 479 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 480 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 481 | 17
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 482 | 112
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 483 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 484 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 485 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 486 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 487 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 488 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 489 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 490 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 491 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 492 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 493 | 98
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 494 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 495 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 496 | 81
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 497 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 498 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 499 | 17
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 500 | 19

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic excavator
Data Collector |  | Yared Girmaw | Data Count | 7 |  | Date | 06_07_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.07 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.07 foeman, 1 opetator, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 11 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 2 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 6.5 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 3 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 11,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 18, 25 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19, 23 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).