## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 101 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 54
|  |  |  | 102 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 103 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 104 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 106 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 107 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 108 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 109 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 110 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 86
|  |  |  | 111 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 112 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 113 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 114 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 115 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 116 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 32
|  |  |  | 117 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 86
|  |  |  | 118 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 119 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 37
|  |  |  | 120 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 123
|  |  |  | 121 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 64
|  |  |  | 122 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 123 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 31
|  |  |  | 124 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 43
|  |  |  | 125 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 126 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 17
|  |  |  | 127 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 128 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 129 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 130 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 131 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 132 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 36
|  |  |  | 133 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 134 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 135 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 136 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 18
|  |  |  | 137 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 73
|  |  |  | 138 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 139 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 140 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 62
|  |  |  | 141 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 41
|  |  |  | 142 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 143 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 36
|  |  |  | 144 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 145 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 146 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 36
|  |  |  | 147 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 148 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 149 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 18
|  |  |  | 150 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 151 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 152 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 37
|  |  |  | 153 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 434 |  |  |  | 408
|  |  |  | 154 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 28
|  |  |  | 155 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 156 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 23
|  |  |  | 157 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 158 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 159 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 160 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 161 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 25
|  |  |  | 162 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 69
|  |  |  | 163 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 164 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 165 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 19
|  |  |  | 166 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 167 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 168 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 83
|  |  |  | 169 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 72
|  |  |  | 170 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 171 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 172 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 33
|  |  |  | 173 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 174 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 175 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 176 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 53
|  |  |  | 177 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 178 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 179 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 180 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 181 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 182 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 183 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 184 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 185 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 186 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 27
|  |  |  | 187 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 68
|  |  |  | 188 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 24
|  |  |  | 189 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 190 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 35
|  |  |  | 191 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 46
|  |  |  | 192 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 29
|  |  |  | 193 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 61
|  |  |  | 194 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 53
|  |  |  | 195 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 49
|  |  |  | 196 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 72
|  |  |  | 197 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 21
|  |  |  | 198 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 22
|  |  |  | 199 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 20
|  |  |  | 200 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 45 | 1 | 0.54 |  |  | 1.3 | 20
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26
|  |  |  | 105 | 1 operator, 1 helper, 1/11 foreman | Hoe | 01- soft rock excavation using hydraulic excavator |  | sand and gravel | 1 | 180 | 1 | 0.54 |  |  | 1.3 | 26

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 101 | 54
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 102 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 103 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 104 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 105 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 106 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 107 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 108 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 109 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 110 | 86
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 111 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 112 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 113 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 114 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 115 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 116 | 32
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 117 | 86
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 118 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 119 | 37
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 120 | 123
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 121 | 64
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 122 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 123 | 31
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 124 | 43
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 125 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 126 | 17
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 127 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 128 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 129 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 130 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 131 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 132 | 36
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 133 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 134 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 135 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 136 | 18
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 137 | 73
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 138 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 139 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 140 | 62
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 141 | 41
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 142 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 143 | 36
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 144 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 145 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 146 | 36
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 147 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 148 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 149 | 18
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 150 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 151 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 152 | 37
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 153 | 434 |  |  | 408
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 154 | 28
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 155 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 156 | 23
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 157 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 158 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 159 | 26
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 160 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 161 | 25
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 162 | 69
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 163 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 164 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 165 | 19
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 166 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 167 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 168 | 83
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 169 | 72
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 170 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 171 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 172 | 33
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 173 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 174 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 175 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 176 | 53
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 177 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 178 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 179 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 180 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 181 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 182 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 183 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 184 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 185 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 186 | 27
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 187 | 68
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 188 | 24
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 189 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 190 | 35
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 191 | 46
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 192 | 29
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 193 | 61
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 194 | 53
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 195 | 49
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 196 | 72
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 197 | 21
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 198 | 22
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 199 | 20
17_05_2017 | 1 | Cherinet Bisetegn | second |  | hydraulic excavator | 200 | 20

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 01- soft rock excavation using hydraulic excavator
Data Collector |  | Cherinet Bisetegn | Data Count | 12 |  | Date | 17_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | observation | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | observation | 1 operator, 1 helper, 1/11 foreman | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 3 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 8 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | ask | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | ask | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | ask | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | ask | 13 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | ask | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | ask | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | observation | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 1 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 11,19 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 17,23 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 28,29 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 40 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).