## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 201 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 202 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 203 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 204 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 206 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 207 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 208 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 209 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 254 |  |  |  |  | 235
|  |  |  | 210 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 211 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 41
|  |  |  | 212 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 213 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 214 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 215 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 216 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 217 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 218 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 32
|  |  |  | 219 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 220 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 305 |  |  |  | 181
|  |  |  | 221 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 222 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 223 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 224 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 225 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 226 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 227 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 228 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 229 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 230 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 147 |  |  |  |  | 123
|  |  |  | 231 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 232 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 233 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 234 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 235 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 236 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 237 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 45 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 238 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 45 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 239 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 85 |  |  |  |  | 63
|  |  |  | 240 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 241 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 242 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 243 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 43
|  |  |  | 244 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 245 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 246 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 247 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 248 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 249 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 102 |  |  |  |  | 83
|  |  |  | 250 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 251 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 252 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 253 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 254 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 255 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 256 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 257 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 258 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 259 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 290 | [5 empty] | 267
|  |  |  | 260 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 261 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 262 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 263 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 264 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 265 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 266 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 267 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 268 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 269 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 270 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 178 |  |  |  | 159
|  |  |  | 271 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 272 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 273 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 274 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 275 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 1 |  |  | 1 | 26
|  |  |  | 276 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 277 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 278 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 279 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 437 |  |  |  | 415
|  |  |  | 280 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 281 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 282 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 283 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 284 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 285 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 286 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 287 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 288 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 394 |  |  |  |  | 373
|  |  |  | 289 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 290 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 291 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 292 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 293 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 294 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 60 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 295 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 296 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 297 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 286 |  |  |  |  | 263
|  |  |  | 298 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 299 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 300 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 205 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 201 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 202 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 203 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 204 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 205 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 206 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 207 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 208 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 209 | 254 |  |  |  | 235
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 210 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 211 | 41
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 212 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 213 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 214 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 215 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 216 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 217 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 218 | 32
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 219 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 220 | 305 |  |  | 181
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 221 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 222 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 223 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 224 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 225 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 226 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 227 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 228 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 229 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 230 | 147 |  |  |  | 123
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 231 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 232 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 233 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 234 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 235 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 236 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 237 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 238 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 239 | 85 |  |  |  | 63
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 240 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 241 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 242 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 243 | 43
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 244 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 245 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 246 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 247 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 248 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 249 | 102 |  |  |  | 83
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 250 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 251 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 252 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 253 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 254 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 255 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 256 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 257 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 258 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 259 | 290 |  |  |  |  | 267
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 260 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 261 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 262 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 263 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 264 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 265 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 266 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 267 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 268 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 269 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 270 | 178 |  |  | 159
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 271 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 272 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 273 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 274 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 275 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 276 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 277 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 278 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 279 | 437 |  |  | 415
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 280 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 281 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 282 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 283 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 284 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 285 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 286 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 287 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 288 | 394 |  |  |  | 373
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 289 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 290 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 291 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 292 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 293 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 294 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 295 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 296 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 297 | 286 |  |  |  | 263
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 298 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 299 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 300 | 19

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 01 rock excavation using hydraulic excavator
Data Collector |  | Temesgen Atalay | Data Count | 1 |  | Date | 22_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 1/10 foreman 1 helper, 1 operator | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | record | 50 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | asking | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | observation | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | record | 0.42 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | count | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 8,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 53,60 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | record | 0 | Range (0 -38) | Over all project activities (besides the one under study).