## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
28_05_2017 | 1 | Yared Girmaw | 2 | 1 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 27 | 1.9021
|  |  |  | 2 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 3 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 23
|  |  |  | 4 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 6 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 27
|  |  |  | 7 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 66
|  |  |  | 8 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 9 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 29
|  |  |  | 10 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 31
|  |  |  | 11 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 30
|  |  |  | 12 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 13 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 14 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 82
|  |  |  | 15 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 23
|  |  |  | 16 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 22
|  |  |  | 17 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 18 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 19 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 20 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 21 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 22 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 23 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 24 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 71
|  |  |  | 25 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 30
|  |  |  | 26 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 23
|  |  |  | 27 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 28
|  |  |  | 28 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 14
|  |  |  | 29 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 30 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 31 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 109
|  |  |  | 32 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 19
|  |  |  | 33 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 34 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 35 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 21
|  |  |  | 36 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 37 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 0.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 38 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 0.5 | 0.53 |  |  | 1.7 | 475 |  |  |  |  | 450
|  |  |  | 39 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 0.5 | 0.53 |  |  | 1.7 | 30
|  |  |  | 40 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 0.5 | 0.53 |  |  | 1.7 | 34
|  |  |  | 41 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 0.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 42 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 0.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 43 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 56
|  |  |  | 44 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 45 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 46 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 47 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 48 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 33
|  |  |  | 49 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 109
|  |  |  | 50 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 28
|  |  |  | 51 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 52 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 53 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 54 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 55 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 28
|  |  |  | 56 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 57 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 58 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 181
|  |  |  | 59 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 28
|  |  |  | 60 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 18
|  |  |  | 61 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 62 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 63 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 64 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 27
|  |  |  | 65 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 66 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 117
|  |  |  | 67 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 32
|  |  |  | 68 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 69 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 70 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 71 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 72 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.5 | 0.53 |  |  | 1.7 | 31
|  |  |  | 73 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 96
|  |  |  | 74 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 17
|  |  |  | 75 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 21
|  |  |  | 76 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 77 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 78 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 22
|  |  |  | 79 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 25
|  |  |  | 80 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 24
|  |  |  | 81 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 82 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 83 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 84 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 18
|  |  |  | 85 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 86 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 87 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 17
|  |  |  | 88 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 103
|  |  |  | 89 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 90 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 21
|  |  |  | 91 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 92 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 93 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 15
|  |  |  | 94 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 121
|  |  |  | 95 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 45 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 96 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 97 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 98 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.2 | 0.53 |  |  | 1.7 | 32
|  |  |  | 99 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 100 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 60 | 1.2 | 0.53 |  |  | 1.7 | 20
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 5 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1 | 0.53 |  |  | 1.7 | 25

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 1 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 2 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 3 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 4 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 5 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 6 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 7 | 66
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 8 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 9 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 10 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 11 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 12 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 13 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 14 | 82
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 15 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 16 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 17 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 18 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 19 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 20 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 21 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 22 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 23 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 24 | 71
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 25 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 26 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 27 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 28 | 14
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 29 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 30 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 31 | 109
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 32 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 33 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 34 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 35 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 36 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 37 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 38 | 475 |  |  |  | 450
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 39 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 40 | 34
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 41 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 42 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 43 | 56
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 44 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 45 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 46 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 47 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 48 | 33
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 49 | 109
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 50 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 51 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 52 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 53 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 54 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 55 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 56 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 57 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 58 | 181
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 59 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 60 | 18
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 61 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 62 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 63 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 64 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 65 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 66 | 117
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 67 | 32
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 68 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 69 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 70 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 71 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 72 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 73 | 96
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 74 | 17
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 75 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 76 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 77 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 78 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 79 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 80 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 81 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 82 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 83 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 84 | 18
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 85 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 86 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 87 | 17
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 88 | 103
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 89 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 90 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 91 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 92 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 93 | 15
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 94 | 121
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 95 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 96 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 97 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 98 | 32
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 99 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 100 | 20

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic exvavator
Data Collector |  | Yared Girmaw | Data Count | 2 |  | Date | 28_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.083 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.08 foreman, 1 op, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | count | 15 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 12 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 2 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 5 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 18 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 5 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 10,24 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 50,67 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 18,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).