## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
|  |  |  | 201 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 21
|  |  |  | 202 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 22
|  |  |  | 203 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 21
|  |  |  | 204 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 22
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 206 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 207 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 120
|  |  |  | 208 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 209 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 210 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 30
|  |  |  | 211 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 29
|  |  |  | 212 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 30
|  |  |  | 213 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 214 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 215 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 91
|  |  |  | 216 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 217 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 218 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 19
|  |  |  | 219 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 220 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 17
|  |  |  | 221 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 222 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 78
|  |  |  | 223 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 224 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 225 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 226 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 227 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 228 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 79
|  |  |  | 229 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 21
|  |  |  | 230 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 22
|  |  |  | 231 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 0.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 232 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 0.5 | 0.53 |  |  | 1.7 | 27
|  |  |  | 233 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 0.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 234 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 0.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 235 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1 | 0.53 |  |  | 1.7 | 81
|  |  |  | 236 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1 | 0.53 |  |  | 1.7 | 27
|  |  |  | 237 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1 | 0.53 |  |  | 1.7 | 24
|  |  |  | 238 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 239 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 160 | 1 | 0.53 |  |  | 1.7 | 26
|  |  |  | 240 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 30
|  |  |  | 241 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 122
|  |  |  | 242 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 31
|  |  |  | 243 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 244 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 30
|  |  |  | 245 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 246 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 247 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 248 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 29
|  |  |  | 249 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 97
|  |  |  | 250 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 26
|  |  |  | 251 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 252 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 253 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 254 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 255 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 20
|  |  |  | 256 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 1009 |  |  |  |  | 978
|  |  |  | 257 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 258 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 78
|  |  |  | 259 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 260 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 21
|  |  |  | 261 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 262 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 263 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 264 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 265 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 266 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1 | 0.53 |  |  | 1.7 | 69
|  |  |  | 267 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1 | 0.53 |  |  | 1.7 | 25
|  |  |  | 268 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1 | 0.53 |  |  | 1.7 | 30
|  |  |  | 269 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1 | 0.53 |  |  | 1.7 | 29
|  |  |  | 270 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1 | 0.53 |  |  | 1.7 | 27
|  |  |  | 271 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.5 | 0.53 |  |  | 1.7 | 32
|  |  |  | 272 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 273 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.5 | 0.53 |  |  | 1.7 | 26
|  |  |  | 274 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 22
|  |  |  | 275 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 21
|  |  |  | 276 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.5 | 0.53 |  |  | 1.7 | 23
|  |  |  | 277 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 278 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 28
|  |  |  | 279 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 22
|  |  |  | 280 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 30
|  |  |  | 281 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 78
|  |  |  | 282 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 25
|  |  |  | 283 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 31
|  |  |  | 284 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 285 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.7 | 0.53 |  |  | 1.7 | 27
|  |  |  | 286 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.7 | 0.53 |  |  | 1.7 | 23
|  |  |  | 287 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.7 | 0.53 |  |  | 1.7 | 74
|  |  |  | 288 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1.7 | 0.53 |  |  | 1.7 | 39
|  |  |  | 289 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.5 | 0.53 |  |  | 1.7 | 36
|  |  |  | 290 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 291 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.5 | 0.53 |  |  | 1.7 | 25
|  |  |  | 292 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.2 | 0.53 |  |  | 1.7 | 41
|  |  |  | 293 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.2 | 0.53 |  |  | 1.7 | 111
|  |  |  | 294 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.2 | 0.53 |  |  | 1.7 | 68
|  |  |  | 295 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.2 | 0.53 |  |  | 1.7 | 26
|  |  |  | 296 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 120 | 1.2 | 0.53 |  |  | 1.7 | 19
|  |  |  | 297 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.5 | 0.53 |  |  | 1.7 | 24
|  |  |  | 298 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.2 | 0.53 |  |  | 1.7 | 28
|  |  |  | 299 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.2 | 0.53 |  |  | 1.7 | 37
|  |  |  | 300 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 180 | 1.2 | 0.53 |  |  | 1.7 | 23
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20
|  |  |  | 205 | 1/12 foreman,1 operator, 1helper | Hoe | soft rock excavation using hydraulic exvavator |  | clay and gravel | 0.95 | 90 | 1 | 0.53 |  |  | 1.7 | 20

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 201 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 202 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 203 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 204 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 205 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 206 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 207 | 120
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 208 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 209 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 210 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 211 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 212 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 213 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 214 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 215 | 91
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 216 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 217 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 218 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 219 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 220 | 17
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 221 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 222 | 78
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 223 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 224 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 225 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 226 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 227 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 228 | 79
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 229 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 230 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 231 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 232 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 233 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 234 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 235 | 81
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 236 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 237 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 238 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 239 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 240 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 241 | 122
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 242 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 243 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 244 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 245 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 246 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 247 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 248 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 249 | 97
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 250 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 251 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 252 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 253 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 254 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 255 | 20
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 256 | 1009 |  |  |  | 978
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 257 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 258 | 78
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 259 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 260 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 261 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 262 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 263 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 264 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 265 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 266 | 69
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 267 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 268 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 269 | 29
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 270 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 271 | 32
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 272 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 273 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 274 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 275 | 21
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 276 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 277 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 278 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 279 | 22
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 280 | 30
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 281 | 78
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 282 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 283 | 31
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 284 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 285 | 27
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 286 | 23
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 287 | 74
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 288 | 39
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 289 | 36
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 290 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 291 | 25
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 292 | 41
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 293 | 111
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 294 | 68
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 295 | 26
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 296 | 19
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 297 | 24
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 298 | 28
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 299 | 37
28_05_2017 | 1 | Yared Girmaw | second |  | hydraulic excavation | 300 | 23

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic exvavator
Data Collector |  | Yared Girmaw | Data Count | 2 |  | Date | 28_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.083 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.08 foreman, 1 op, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | count | 15 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 3 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 4 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 12 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 2 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 5 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 18 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 5 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 10,24 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 50,67 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 18,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 60 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).