## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
06-07-2017 | 1 | Yared Girma | 2 | 101 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 102 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 103 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 23
|  |  |  | 104 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 95
|  |  |  | 105 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 20
|  |  |  | 106 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 23
|  |  |  | 107 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 28
|  |  |  | 108 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 40
|  |  |  | 109 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 21
|  |  |  | 110 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 19
|  |  |  | 111 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.5 | 0.61 |  |  | 1.3 | 107
|  |  |  | 112 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.5 | 0.61 |  |  | 1.3 | 31
|  |  |  | 113 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.5 | 0.61 |  |  | 1.3 | 40
|  |  |  | 114 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 115 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 18
|  |  |  | 116 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 20
|  |  |  | 117 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 118 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 119 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 381 | [5 empty] | 360
|  |  |  | 120 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 73
|  |  |  | 121 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 31
|  |  |  | 122 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 123 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 124 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 125 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 33
|  |  |  | 126 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 29
|  |  |  | 127 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 128 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 129 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 20
|  |  |  | 130 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 22
|  |  |  | 131 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 33
|  |  |  | 132 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 133 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 118
|  |  |  | 134 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 49
|  |  |  | 135 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 30
|  |  |  | 136 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 22
|  |  |  | 137 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 37
|  |  |  | 138 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 139 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 45
|  |  |  | 140 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 28
|  |  |  | 141 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 44
|  |  |  | 142 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 123
|  |  |  | 143 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 22
|  |  |  | 144 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 145 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 23
|  |  |  | 146 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 23
|  |  |  | 147 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 148 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 24
|  |  |  | 149 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 150 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.7 | 0.61 |  |  | 1.3 | 31
|  |  |  | 151 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 100 | 2.7 | 0.61 |  |  | 1.3 | 21
|  |  |  | 152 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 25
|  |  |  | 153 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 72
|  |  |  | 154 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 32
|  |  |  | 155 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 156 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 157 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 28
|  |  |  | 158 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 29
|  |  |  | 159 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 31
|  |  |  | 160 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 103
|  |  |  | 161 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 25
|  |  |  | 162 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26
|  |  |  | 163 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 27
|  |  |  | 164 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 21
|  |  |  | 165 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 20
|  |  |  | 166 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 22
|  |  |  | 167 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 21
|  |  |  | 168 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 169 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 23
|  |  |  | 170 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 171 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 172 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 173 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 98
|  |  |  | 174 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 175 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 176 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 177 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 26
|  |  |  | 178 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 29
|  |  |  | 179 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 31
|  |  |  | 180 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 36
|  |  |  | 181 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 28
|  |  |  | 182 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 79
|  |  |  | 183 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 25
|  |  |  | 184 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 27
|  |  |  | 185 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 160 | 3 | 0.61 |  |  | 1.3 | 32
|  |  |  | 186 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 28
|  |  |  | 187 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 188 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 189 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 26
|  |  |  | 190 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 31
|  |  |  | 191 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 30
|  |  |  | 192 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 92
|  |  |  | 193 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 194 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 29
|  |  |  | 195 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 30
|  |  |  | 196 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 31
|  |  |  | 197 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 27
|  |  |  | 198 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 25
|  |  |  | 199 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 120 | 2.7 | 0.61 |  |  | 1.3 | 24
|  |  |  | 200 | 1/14 foreman:1 opetator ,1 helper | Hoe | soft rock excavation using hydraulic excavator |  | soft rock | 0.75 | 90 | 3.5 | 0.61 |  |  | 1.3 | 26

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
06-07-2017 | 1 | Yared Girma | second |  | hydraulic excavator's | 101 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 102 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 103 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 104 | 95
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 105 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 106 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 107 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 108 | 40
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 109 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 110 | 19
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 111 | 107
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 112 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 113 | 40
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 114 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 115 | 18
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 116 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 117 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 118 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 119 | 381 |  |  |  |  | 360
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 120 | 73
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 121 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 122 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 123 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 124 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 125 | 33
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 126 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 127 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 128 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 129 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 130 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 131 | 33
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 132 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 133 | 118
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 134 | 49
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 135 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 136 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 137 | 37
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 138 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 139 | 45
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 140 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 141 | 44
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 142 | 123
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 143 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 144 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 145 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 146 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 147 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 148 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 149 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 150 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 151 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 152 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 153 | 72
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 154 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 155 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 156 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 157 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 158 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 159 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 160 | 103
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 161 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 162 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 163 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 164 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 165 | 20
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 166 | 22
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 167 | 21
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 168 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 169 | 23
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 170 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 171 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 172 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 173 | 98
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 174 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 175 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 176 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 177 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 178 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 179 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 180 | 36
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 181 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 182 | 79
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 183 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 184 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 185 | 32
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 186 | 28
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 187 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 188 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 189 | 26
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 190 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 191 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 192 | 92
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 193 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 194 | 29
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 195 | 30
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 196 | 31
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 197 | 27
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 198 | 25
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 199 | 24
06_07_2017 | 1 | Yared Girmaw | second |  | hydraulic excavator's | 200 | 26

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | soft rock excavation using hydraulic excavator
Data Collector |  | Yared Girmaw | Data Count | 7 |  | Date | 06_07_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 2.07 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 0.07 foeman, 1 opetator, 1 helper | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | observation | 11 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 2 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | observation | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | asking | 2 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 2 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | count | 6.5 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | observation | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 3 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 11,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 18, 25 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19, 23 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | observation | 0 | Range (0 -38) | Over all project activities (besides the one under study).