## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
22_05_2017 | 1 | Temesgen Atalay | 1 | 1 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 1823 | 0.015058 |  |  |  |  | 1800
|  |  |  | 2 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 3 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 4 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 5 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 6 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 28
|  |  |  | 7 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 25
|  |  |  | 8 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 28
|  |  |  | 9 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 42
|  |  |  | 10 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 15
|  |  |  | 11 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 65
|  |  |  | 12 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 35
|  |  |  | 13 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 14 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 27
|  |  |  | 15 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 16 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 20
|  |  |  | 17 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 27
|  |  |  | 18 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 19 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 20 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 21 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 309 |  |  |  |  | 285
|  |  |  | 22 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 20
|  |  |  | 23 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 24 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 25 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 29
|  |  |  | 26 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 27 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 17
|  |  |  | 28 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 218 |  |  |  |  | 198
|  |  |  | 29 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 20
|  |  |  | 30 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 31 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 32 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 29
|  |  |  | 33 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 34 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 20
|  |  |  | 35 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 36 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 37 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 38 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 29
|  |  |  | 39 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 27
|  |  |  | 40 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 41 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 42 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 43 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 34
|  |  |  | 44 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 45 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 29
|  |  |  | 46 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 74 |  |  |  |  | 52
|  |  |  | 47 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 48 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 49 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 50 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 51 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 52 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 17
|  |  |  | 53 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 54 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 55 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 56 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 84 |  |  |  |  | 63
|  |  |  | 57 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 17
|  |  |  | 58 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 59 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 60 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 61 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 17
|  |  |  | 62 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 63 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 64 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 65 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 99 |  |  |  |  | 76
|  |  |  | 66 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 150 | 0.5 | 0.61 |  |  | 1 | 28
|  |  |  | 67 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 150 | 0.5 | 0.61 |  |  | 1 | 30
|  |  |  | 68 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 69 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 70 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 71 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 46
|  |  |  | 72 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 28
|  |  |  | 73 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 69 |  |  |  |  | 49
|  |  |  | 74 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 75 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 76 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 77 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 22
|  |  |  | 78 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 79 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 80 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 36
|  |  |  | 81 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 23
|  |  |  | 82 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 24
|  |  |  | 83 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 153 |  |  |  |  | 131
|  |  |  | 84 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 20
|  |  |  | 85 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 86 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 21
|  |  |  | 87 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 88 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 89 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 90 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 91 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 17
|  |  |  | 92 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 93 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 186 |  |  |  |  | 170
|  |  |  | 94 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 25
|  |  |  | 95 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 16
|  |  |  | 96 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 97 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 31
|  |  |  | 98 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 100 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 99 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 26
|  |  |  | 100 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 30

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 1 | 1823 |  |  |  |  | 1800
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 2 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 3 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 4 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 5 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 6 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 7 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 8 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 9 | 42
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 10 | 15
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 11 | 65
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 12 | 35
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 13 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 14 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 15 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 16 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 17 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 18 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 19 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 20 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 21 | 309 |  |  |  | 285
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 22 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 23 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 24 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 25 | 29
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 26 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 27 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 28 | 218 |  |  |  | 198
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 29 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 30 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 31 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 32 | 29
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 33 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 34 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 35 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 36 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 37 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 38 | 29
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 39 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 40 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 41 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 42 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 43 | 34
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 44 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 45 | 29
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 46 | 74 |  |  |  | 52
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 47 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 48 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 49 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 50 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 51 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 52 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 53 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 54 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 55 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 56 | 84 |  |  |  | 63
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 57 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 58 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 59 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 60 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 61 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 62 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 63 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 64 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 65 | 99 |  |  |  | 76
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 66 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 67 | 30
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 68 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 69 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 70 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 71 | 46
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 72 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 73 | 69 |  |  |  | 49
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 74 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 75 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 76 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 77 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 78 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 79 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 80 | 36
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 81 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 82 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 83 | 153 |  |  |  | 131
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 84 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 85 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 86 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 87 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 88 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 89 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 90 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 91 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 92 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 93 | 186 |  |  |  | 170
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 94 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 95 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 96 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 97 | 31
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 98 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 99 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 100 | 30

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 01 rock excavation using hydraulic excavator
Data Collector |  | Temesgen Atalay | Data Count | 1 |  | Date | 22_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 1/10 foreman 1 helper, 1 operator | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | record | 50 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | asking | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | observation | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | record | 0.42 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | count | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 8,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 53,60 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | record | 0 | Range (0 -38) | Over all project activities (besides the one under study).