## excavator
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Excavator Productivity Data Records
|  |  |  | Form - 1 | [14 empty] | MPDM - Delay
[10 empty] | Factors | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6
Date: | Project Code: | Data Collector | Number of Equipment Types: | Excavator Cycle | Manpower (Foreman, Operator, Helper, Laborers, etc.) | Excavator Type (Face Shovel, Hoe, Loader) | Task Type | Description | Soil Type | F (Bucket Fill Factor) | AS (Angle of Swing ) | D (Depth of Cut) | Volume Correction | Efficiency | Unit | Q Heaped Bucket Capcity (m3) | T Cycle Time (seconds) | Productivity (m3/hr) | Enviroment | Equipment | Labour | Material | Management | Others
22-05-2017 | 1 | Temesgen Atalay | 1 | 301 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 302 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 30
|  |  |  | 303 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 304 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 305 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 306 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 307 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 313 |  |  |  |  | 291
|  |  |  | 308 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 309 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 310 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 311 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 312 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 313 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 314 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 315 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 316 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 89 |  |  |  |  | 67
|  |  |  | 317 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 318 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 319 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 320 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 321 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 322 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 323 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 324 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 93 |  |  |  |  | 74
|  |  |  | 325 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 326 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 29
|  |  |  | 327 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 328 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 329 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 330 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 331 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 332 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 17
|  |  |  | 333 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 817 |  |  |  | 794
|  |  |  | 334 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 335 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 336 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 337 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 338 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 339 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 340 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 341 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 342 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 343 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 413 |  |  |  |  | 391
|  |  |  | 344 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 345 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 346 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 347 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 348 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 349 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 350 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 351 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 352 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 353 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 83 |  |  |  |  | 60
|  |  |  | 354 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 355 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 356 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 357 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 358 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 359 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 360 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 361 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 362 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 363 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 385 |  |  |  |  | 363
|  |  |  | 364 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 365 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 366 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 367 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 368 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 369 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 370 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 371 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 372 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 373 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 419 |  |  |  | 295
|  |  |  | 374 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 28
|  |  |  | 375 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 376 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 377 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 378 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 20
|  |  |  | 379 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 21
|  |  |  | 380 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 381 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 382 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 383 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 115 |  |  |  |  | 94
|  |  |  | 384 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 22
|  |  |  | 385 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 386 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 387 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 388 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 23
|  |  |  | 389 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 16
|  |  |  | 390 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 19
|  |  |  | 391 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 90 | 0.5 | 0.61 |  |  | 1 | 18
|  |  |  | 392 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 87 |  |  |  |  | 63
|  |  |  | 393 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 394 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 24
|  |  |  | 395 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 19
|  |  |  | 396 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 120 | 1 | 0.61 |  |  | 1 | 18
|  |  |  | 397 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 27
|  |  |  | 398 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 25
|  |  |  | 399 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 26
|  |  |  | 400 | 1/10 foreman 1 helper, 1 operator | Hoe | 01 rock excavation using hydraulic excavator |  | rock | 0.75 | 180 | 1 | 0.61 |  |  | 1 | 19

## mpdm
Construction Management Institute
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
MPDM Data Sheet Form
Form - 4
Delay
Date: | Project Code: | Data Collector | Unit of Time: | Operation: | Equipment: | Production Cycle Number | Cycle Time | Enviroment | Equipment | Labour | Material | Management | Others
22-05-2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 301 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 302 | 30
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 303 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 304 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 305 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 306 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 307 | 313 |  |  |  | 291
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 308 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 309 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 310 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 311 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 312 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 313 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 314 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 315 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 316 | 89 |  |  |  | 67
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 317 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 318 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 319 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 320 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 321 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 322 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 323 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 324 | 93 |  |  |  | 74
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 325 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 326 | 29
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 327 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 328 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 329 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 330 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 331 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 332 | 17
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 333 | 817 |  |  | 794
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 334 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 335 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 336 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 337 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 338 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 339 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 340 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 341 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 342 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 343 | 413 |  |  |  | 391
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 344 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 345 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 346 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 347 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 348 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 349 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 350 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 351 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 352 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 353 | 83 |  |  |  | 60
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 354 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 355 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 356 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 357 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 358 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 359 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 360 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 361 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 362 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 363 | 385 |  |  |  | 363
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 364 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 365 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 366 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 367 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 368 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 369 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 370 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 371 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 372 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 373 | 419 |  |  | 295
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 374 | 28
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 375 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 376 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 377 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 378 | 20
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 379 | 21
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 380 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 381 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 382 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 383 | 115 |  |  |  | 94
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 384 | 22
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 385 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 386 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 387 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 388 | 23
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 389 | 16
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 390 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 391 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 392 | 87 |  |  |  | 63
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 393 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 394 | 24
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 395 | 19
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 396 | 18
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 397 | 27
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 398 | 25
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 399 | 26
22_05_2017 | 1 | Temesgen Atalay | second |  | hydraulic excavator | 400 | 19

## daily_variables
BAHIR DAR INTITUTE OF TECHNOLOGY
PREPARATION OF NATIONAL PRODUCTIVITY NORM FOR WATER CONSTRUCTION TRADE
Form - 6 - Daily Input Variables
Project Code |  | 1 | Task/particular | 01 rock excavation using hydraulic excavator
Data Collector |  | Temesgen Atalay | Data Count | 1 |  | Date | 22_05_2017
Main Factor | Factor ID | Sub - Factors | Scale of Measure | Data Source | Data Value | Sub-factor / Range of Value | Predetermined Ratings (1 - 5) / Description
1. Labour Characterstics |  | Crew Properties
| 1.1 | Crew size | Integer (Total number of crew members) | count | 3 | Range (1 - 20) | Vaules for each of the crews understudy
| 1.2 | Crew composition | Crew Member's Number (Foreman, Tradesperson, Laborer, Helper) | count | 1/10 foreman 1 helper, 1 operator | Range og each category (0 - 10) | Vaules for each of the crews understudy
| 1.3 | Co-operation among craftsperson | 1 - 5 Predetermined rating | observation | 4 | Crew size, Crew heterogeneity in nationality, ability to perform the task, and stake value related to the task | 1. VERY DIVERSE Ability, VERY LOW Stake Value, VERY LARGE Crew Size; 2. DIVERSE Ability, LOW Stake Value, LARGE Crew size; 3. DIVERSE Ability, MEDIUM Stake Value, AVERAGE Crew Size; 4. SIMILAR Ability, HIGH Stake Value, SMALL Crew Size; 5. SIMILAR Ability, VERY HIGH Stake Value, VERY SMALL Crew Size
| 1.4 | Level of interruption and disruption | Integer (Number of interruption and disruption per day) | record | 50 | Range (0 - 20) | To document the number of delay events caused due to several reasons which may disrupt the crew from performing the assigned tasks.
| 1.5 | Fairness of work assignment | 1 - 5 Predetermined rating | observation | 4 | Consistency (same policy), Reasonableness (use of common sense), Resource (resource allocations), Information (provision of information), Timeliness (timely action), Meaningful assignment | 1. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, VERY POOR Information provision; 2. Inconsistent work assignment on a daily basis, Unreasonable work assignment among crew members, POOR Information provision; 3. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, AVERAGE Information provision; 4. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, GOOD Information provision; 5. Consistent work assignment on a daily basis, Reasonable work assignment among crew members, VERY GOOD Information provision
Crew flexibility
| 1.7 | Ability of crew to perform other's task | Percent (degree of ability to perform other's task) | observation | 3 |  | 1. Below 20%; 2. Between 20 - 40%; 3. Between 40 - 60%; 4. Between 60 - 80%; 5. Above 80%
| 1.8 | Willingness to perform other's tasks | Categorical | asking | 3 |  | 1. Completely Unwilling; 2. Somewhat NOT Willing; 3. Somewhat Willing; 4. Willing; 5. Completely Willing
Crew Characterstics
| 1.9 | Craftsperson education | Categorical (Most frequent category) | asking | 2 | Elementary, High School, Technical, College, University | 1 Elementary, 2. Highschool, 3. Technical, 4. College, 5. University
| 1.1 | Craftsperson on job training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 150)
| 1.11 | Craftsperson technical training | Real number (No. trainings attended x Duration of Training, hrs) | observation | 0 | Range (0 - 1000)
| 1.12 | Crew experience (seniority) | Real number (Crew average years of experience ) | asking | 11 | Range (0 - 40)
| 1.13 | Number of languages spoken | Integer (Number of languages spoken, total for a crew) | asking | 1 | Range (1 - 5)
| 1.14 | Job security | Integer (Average length of unemployment period, months) | observation | 0 | Range (0 -12) | Average per crew member.
2. Equipment and Tools |  | Availability of work equipment
| 2.1 | Equipment number` | Categorical (Type and Number on site) | count | 1 | Range (0 - 10) | Work of equipment (crane, forklift)
| 2.2 | Waiting time for work equipment | Real number (Average waiting time,min) | record | 0.42 | Range (0 - 60)
Availability of transport equipment
| 2.3 | Equipment number | Categorical (Type and Number on site) | count | 0 | Range (0 - 10) | Transport equipment (man lift)
| 2.4 | Waiting time for transport equipment | Real number (Average waiting time,min) | observation | 0 | Range (0 - 60)
| 2.5 | Misplacement of tools | Real Number (Average no. of misplacement per day) | observation | 1 | Range (1 - 20)
| 2.6 | Availability of electric power | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
| 2.7 | Availability of extension cords | Real number (Average waiting time,min) | observation | 0 | Range (0 - 30)
3. Project Condition | 3.1 | Weather (temperature) | Real number (˚C) | record | 8,20 | Range: recorded (min, max) | weather.gc.ca.
| 3.2 | Weather (precipitation) | Real number (mm) | record | 0 | Range: recorded (min, max) | weather.gc.ca.
| 3.3 | Weather (humidity) | Real number (%) | record | 53,60 | Range: recorded (min, max) | weather.gc.ca.
| 3.4 | Weather (wind speed) | Real number (km/hr) | record | 19,25 | Range: recorded (min, max) | weather.gc.ca.
| 3.6 | Site congestion | Real number (Ratio free site space to total site area) | observation | 65 | Range (0 -100)
| 3.7 | Use of overtime | Real number (Average over time per week) | record | 0 | Range (0 -38) | Over all project activities (besides the one under study).